| # Request for Quotation GEN3.0 & 3.3 BMU replacement BorgWarner Battery Systems Seneca, SC |  |
| --- | --- |

borgwarner.com

Table of Content

1	BorgWarner Contacts	4

2	Statement of Compliance	4

3	Proprietary Material	4

4	Background of Project	4

5	Project Timeline	4

6	Intent of the Specification	5

7	Project Requirements	5

8	Product Information	6

9	Machine General Specifications	6

9.1.1	UL Certification	6

9.1.2	Utilities Approval	6

9.1.3	Energy Considerations	7

9.2	Operational Manuals	7

9.3	Electrical	7

10	Machine Acceptance Criteria	7

11	Quotation Deliverables	8

Change documentation

| Number | Page / section | Description | Date | Sign |
| --- | --- | --- | --- | --- |
| 0 | All | Initial Release | 05/04/2026 | John Evans |

# BorgWarner Contacts

| Title | Name | Phone Number | Email |
| --- | --- | --- | --- |
| Sr. Manufacturing Engineer | John Evans | +1 (864) 540-6389 | johevans@borgwarner.com |
| Manufacturing Engineering Manager | Marcos Servilla | +1 (864) 795-0075 | mservilla@borgwarner.com |
| Senior Buyer | Wayne Wyant | +1 (864) 710-3601 | wwyant@borgwarner.com |

# Statement of Compliance

The Bidder shall submit a proposal that must include a copy of this specification acknowledging compliance with all sections in the space provided below. A signature or company stamp is acceptable. Any exception to these specifications shall be listed by the Bidder, specifically noted by paragraph number, and then completely detailed in the exceptions sheet below and the Bidder’s proposal.

# Proprietary Material

All information in this inquiry shall be considered confidential to BorgWarner. The information contained in these documents shall not be duplicated, disclosed, or used in whole or in part for other purposes without written permission from BorgWarner Global Purchasing. The terms of the NDA signed between the vendor and BorgWarner apply.

# Background of Project

BorgWarner, Seneca, South Carolina is launching a new battery system part type that requires a new BMU to interface between the modules testers and the battery module (product).

This RFQ pertains to a new BMU that will be implemented within the Seica T20 testers (2), H-KON ILT2 leak testers (20), and H-KON EOL testers (3).

# Project Timeline

The project must be completed and functioning on all testers no later than August 3rd, 2026. To achieve this target, the following timeline is proposed:

| BMU replacement timing |  |  |  |
| --- | --- | --- | --- |
| Quote Submission | Proof-of-Concept | Test on-site | SOP |
| May 15, 2026 | June 12, 2026 | July 6, 2026 | August 3, 2026 |

# Intent of the Specification

This equipment specification is intended as a guide for quoting purposes. All specified items are intended as a minimum standard acceptable to BorgWarner.  In no case is the successful bidder to assume the specification relieves him of responsibility for the proper function of the equipment.  The vendor, in submitting the bid, guarantees the functionality of the equipment. Any changes to the specifications that are initiated by BorgWarner will be issued in writing in the form of an addendum. All bidding vendors are required to submit their bids based upon the basic concepts identified by this specification.  As an option, all bidders may also submit alternative concepts in addition to the base concepts.

- All quotes will be in USD currency.

- No part of this specification shall be interpreted as authorizing non-compliance with applicable federal, state, or local standards, regulations, or law.

- The vendor is expected to be in general agreement with the concept or to present exceptions in writing for consideration so that at the time of contract acceptance, there is mutual concurrence of contract feasibility.  With contract acceptance, the vendor assumes total responsibility to engineer, develop and refine the proposed solution as required to meet BorgWarner`s requirements and performance levels as defined in this specification.

- NO PROPRIETARY ITEMS ARE ALLOWED. The same applies to the source code and software details for communication between the BMU replacement and the testers or battery module.

- BorgWarner is receptive to conditions and ideas that will permit building the best solution at the best price, and suggestions to this effect will be so considered.  All changes in these specifications must be in written form and will become effective only when covered by a Purchase Order Amendment.

- No part of this specification is to be interpreted as restricting the vendor from providing products, services, or documentation, which exceeds the requirements of this specification.

- All callouts on prints setup/operating procedures and other written communications will be done in English.

# Project Requirements

- Provide a solution (hardware and software) that allows the testers (ILT1, ILT2, EOL) to communicate with GEN3.0 and GEN3.3 part types.

- Solution must be able to read and write to the CSC board of both part types (both chip types LTC6812 and ADBMS6833).

- Preference is that current CAN commands are used for GEN3.0 (LTC6812 chip). Modified DBC (Modified GEN3_0 DBC.dbc) has been provided with only the CAN messages needed for testers (ILT1, ILT2, EOL).

- For GEN3.3 (ADBMS6833 chip), the preference is to use the same CAN commands as GEN3.0. The BMU replacement would need to detect the chip type of the battery pack, then convert the command appropriately.

- If it is necessary for GEN3.3, the provider can create new CAN commands to use but must include documentation of each command (CAN message and corresponding ISO-SPI message).

- Solution must write data to the locations listed in the Excel layout files:

  - GEN3.0 EEPROM layout (tab “EEPROM Memory Allocation”).

  - GEN3.3 EEPROM layout (tab “EOL Data CSC”).

- Solution must write to the correct location, have the correct length, and have the correct data type.

- Solution must be able to read cell voltages and temperatures for both part types.

- Solution must be a “drop-in” replacement for the current BMU. The new solution cannot increase the cycle time of the tester.

# Product Information

- The product being tested is a battery module.

- The battery module is comprised of 600 cells in two 300 cell “half-packs”.

- The battery module configuration is 20s/30p.

- The GEN3.0 battery module has a CSC board with an LTC6812 ADI chip.

- The GEN3.3 battery module has a CSC board with an ADBMS6833 ADI chip.

- Schematics for each CSC board have been included with the RFQ.

# Machine General Specifications

The system shall be developed to the following standards:

- OSHA, NEMA, DIN, NIOSH, ASME, ANSI, NEC, UL, and other applicable codes and standards CAT 3 Safety

### UL Certification

Bidder will be responsible that equipment will be built according to UL standards.

### Utilities Approval

- Supplier must include information on the following requirements at time of design review approval:

  - Total electrical load

    - Required voltage and frequency

    - Service drop rating

    - Equipment full load amps and peak amp requirements

    - Typical operating load KW

### Energy Considerations

See “50001 Ready Playbook Task 18 Energy Considerations in Design – Design Checklist.docx”

## Operational Manuals

- The supplier shall provide an operation manual in a WORD document format referred to as the Equipment Operating Procedure (EOP).  The EOP provides for the following:

  - Table of contents

  - Description of Equipment

  - Sequence of operations

  - Set up information and instructions

  - Illustrated spare parts list with descriptive information, purchasing source and pricing

  - Detailed schematic drawings to the component level (electrical & mechanical)

  - Recommended list of spare parts.

  - Planned maintenance recommendations & special maintenance instructions.

  - Installation requirements

  - Electronic copy of manual

  - Manuals in manufacturing plant local language and English

  - Trouble-shooting guide.

- As part of the EOP requirements, the supplier shall also provide an operations and maintenance manual in a .pdf document for all mechanical and controls hardware.  This includes all fabricated and purchased subsystems.

- The EOP and the .pdf files will be supplied on a USB.

- All documents will be provided in English

## Electrical

- All electrical design and installations must be in compliance with OSHA 1910, NFPA 70 (NEC), and NFPA 79.

- The available supply voltage is 480VAC 3PH.  120VAC 1PH is available for applications requiring less than 20 amps.

# Machine Acceptance Criteria

The Proof-of-Concept at the Supplier’s facility must be performed to deliver a working solution that will require minimum set-up on the BorgWarner floor. BorgWarner will supply all components needed to complete the Proof-of-Concept. The Proof-of-Concept criteria include the following:

- Live presentation of Solution communicating with GEN3.0 CSC board and GEN3.3 CSC board, including:

  - Reading of cell voltages

  - Reading of cell temperatures

  - Writing data to EEPROM

The Test On-Site at the BorgWarner facility will consist of the same criteria listed above to confirm the functionality of the solution to the same level of performance displayed during the Proof-of-Concept at the Supplier. The Test On-Site will also include:

- Integration of the solution into one Seica T20 tester.

- Integration of the solution into one H-KON ILT2 tester.

- Testing of Solution on production parts.

- Review of Technical compliance to specification.

Within 30 days of SOP at BW the following shall be provided:

- Electronic copy of software – original code on USB.

- 2 hard copies of user manual.

- 1 USB with full documentation delivered 30 days after successful SOP at BW

# Quotation Deliverables

BorgWarner requests a Firm Quotation for the solution that meets the design criteria and deliverables outlined in this RFQ. The supplier shall provide valuation based on this specification and recommend solutions providing options and alternatives that will reduce costs and/or will improve device performance and product quality. If these options are approved, it will be included in the updated specification or attached to the original, as an attachment.

BorgWarner requests the quotation to include at a minimum the following:

- Any additional licenses needed

- Detailed cost breakdown in the following 3 categories:

  - Equipment/hardware cost

  - Software development cost

  - Product support (yearly cost)

- Quotations should be sent no later than May 15, 2026 to the following:

| John Evans Sr. Manufacturing Engineer Email: johevans@borgwarner.com Marcos Servilla Manufacturing Engineering Manager Email: mservilla@borgwarner.com |  | Wayne Wyant Buyer Email: wwyant@borgwarner.com |
| --- | --- | --- |